## Hoja1
Task | Group member | Estimated hours | Final hours
WIKI
Home Page | Alex Campamar | 1h | 1h
Art | David Lozano | 1h | 1h
Sprites | David Lozano | 6h | 18h
Other sprites | Joan Valiente | 4h | 4h
Audio | Alex Campamar | 4h | 6h
Design | TOTORO | - | -
General analysiss | Alex Campamar | 2h | 2h
UI | Joan Valiente | 1h 30 min | 1h 30 min
Revision | Joan Valiente | 2h | 3h
Gunbird 0.1
Module Audio | Joan Valiente | 2h | 4h
Module Player | David Lozano | 2h | 3h
Module Background | Alex Campamar | 3h | 3h
Gunbird 0.2
Module Mine | All | 1h | 1h 30min
Module Sea | All | 30 min | 20 min
Module Welcome | All | 30 min | 20 min
Module Congrats | All | 30 min | 20 min
Add Audio to each levels | Alex Campamar | 30 min | 1h
Gunbird 0.3
Camera limits | ALL | 1h | 1h
Player Animation | David Lozano | 1h | 1h
Background Animation | David Lozano | 30 min | 1 h
Player Shot | Joan Valiente / Alex Campamar | 30 min | 2 h
Gunbird 0.4
Fixed Camera limits | David Lozano | 1h | 2h
Module Colision | Joan Valiente | 2h | 2h
Colliding testing | Alex Campamar | 1h | 1h
Q&A work | Joan Valiente | 1h | 2h
Gunbird 0.5
God Mode | Joan Valiente | 1h | 1h
Enemies Module | Alex Campamar | 1h | 4h
Enemies Animation | David Lozano | 2h | 2h
Explosion Sound | Alex Campamar | 20 min | 20 min
Second Player | Alex Campamar | 2h | 1h
Balloon Shoots | Alex Campamar | 1h | 2h
Added Numbres sprite | David Lozano | 10 min | 10 min
Added Power Up | Joan Valiente | 4h | 6h
Updated Sprites | David Lozano | 1h | 2h
UI | Alex Campamar | 2h | 8h
Player 2 Updated | Joan Valiente | 1h | 3h
Menu Animation | David Lozano | 30 min | 30 min
Updated Explosion animation | David Lozano | 30 min | 1h
Updated colisions | Joan Valiente | 2h | 2h
Updated Animations | David Lozano | 1h | 2h
Score Board Player 2 | David Lozano | 1h | 2h
Background Animations Added | David Lozano | 1h | 2h
Module Path | Alex Campamar | 2h | 3h
Added Enemies with Path | Joan Valiente | 3h | 3h
Added Animations | David Lozano | 30 min | 1h
Win Condition | Alex Campamar | 30 min | 1h
Updated score screen | David Lozano | 1h | 1h
Updated Enemies with Path | Joan Valiente | 3h | 4h
Added Balloon life and hit animation | David Lozano | 20 min | 40 min
Added Enemies to level | Joan Valiente | 3h | 3h
Added Enemies IA | Alex Campamar | 8h | 20 h
Q&A work | Alex Campamar | 6h | 8h
Q&A work | Joan Valiente | 15h | 23h
Q&A work | David Lozano | 10h | 15h
Gunbird 0.6
Shoot burst | Alex Campamar | 2h | 1h
Character Selection Screen | David Lozano | 4h | 8h
Player lives | David Lozano | 3h | 6h
Ash bomb | David Lozano | 1h | 7h
Ash powerups | Alex Campamar | 4h | 3h
Gamepad controll | Joan Valiente | 2h | 5h
Gamepad bugs fixed | Joan Valiente | 5h | 8h
Audio bug | Alex Campamar | 4h | 7h
Continue mode | David Lozano | 2h | 4h
Gunbird 0.7
UI Module | David Lozano | 1h | 1h
Valnus Implemented | David Lozano | 2h | 4h
Blocked characters on character selector | David Lozano | 4h | 4h
Fixed enemy shot | David Lozano | 3h | 5h
Added Enemies Sprites | David Lozano | 3h | 3h
Finally 100% fixed enemy shoot | Alex Campamar | 4h | 10h
Enemy VerticalBomb (first wave) | Joan Valiente | 2h | 2h
Enemy SurfingTowers (first wave) | Joan Valiente | 3h | 3h
Enemy SurfingTowers (second wave) | Joan Valiente | 1h | 1h
Enemy Big Tower | David Lozano | 2h | 2h
Enemy Blue Robot | David Lozano | 4h | 4h
Added all remaining enemies | David Lozano | 7h | 8h
Added All particles | David Lozano | 2h | 2h